## PLan
Activity | Responsibility | Timeframe | Method | Resources | Additional Information
Objective 1: Knowledge management and sharing
Set up an adaptation webpage on the NGORC CCWG website | NGORC | March | Group members to provide content to NGORC | NGORC (website) with input from group members
Link adaptation webpage to relevant websites (eg. group member sites, NDMP, DMWG etc.) | NGORC | March | Group members to source and provide links to NGORC | NGORC (website) with input from group members
Collect information about adaptation activities in Vietnam, best practice and tools/methods | VGBC | Ongoing from March | VGBC to set up online forum | VGBC (website), NGORC to link adaptation webpage, all group members to provide input and promote to other external stakeholders | http://vsccan.org/vnccaforum/
Compile and cirulate a quarterly digest and year-end report on adaptation activities implemented in Vietnam, best practice and tools/methods | VGBC/CARE | First quarterly digest on June 1st, then every 3 months until first annual report on December 1st | VGBC compiles information from the forum site above and authors digests/reports; CARE to coordinate information gathering from government and other external sources. NGO RC CC website for dissemnination | VGBC and CARE with input from other group members
Objective 2: Building NGO capacity (sharing methods and tools)
Conduct group climate change adaptation capacity needs assessment | CARE | April 4th? | Next thematic group meeting; CARE to coordinate assessment with input from all group members | NGORC (venue) with attendance and input from all group members
Plan and prepare for climate change adaptation capacity building events | All | Ongoing from April; one event to be held in 2008 | Identify needs through capacity assessment; planning via regular thematic group meetings; CARE to coordinate preparations with input and support from all group members | NGORC (venue) with attendance and input from all group members.
Identify and share information on climate change adaptation expertise amongst NGOs and other stakeholders | C2C | Ongoing from April | C2C to review stakeholder analysis and report back at next thematic group meeting | C2C
Develop a capacity building sub-page on the adaptation webpage with links to climate change adaptation resources, methods and tools | NGORC | April | NGORC (website) with input from all group members; CARE to coordinate information gathering | NGORC (website) with input from group members
Schedule "learning and sharing" presentations as part of regular thematic group and wider CCWG meetings | C2C/CARE | Ongoing from April | C2C to request NRC to do first presentation at next adaptation thematic group meeting; C2C to seek input from group members by email on future topics and presenters (for finalisation at next group meeting and revised on an ongoing basis); CARE to coordinate schedule of future presentations | C2C with support from CARE and input from all group members
Identify sources of funding for climate change adaptation programming and related NGO capacity building | EMW | April | EMW to gather information and report back at future thematic group meeting | EMW
Identify and share existing capacity building opportunities | CARE | Ongoing from April | CARE to coordinate information gathering at regular thematic group meetings | CARE with input from group members
Objective 3: Advocacy
Identify advocacy agenda | CARE | Ongoing from April | CARE to coordinate information gathering at regular thematic group meetings | CARE with input from group members and policy group
Identify expertise/strengths among NGOs to take a lead on specific advocacy priorities | CARE | Ongoing from April | CARE to coordinate information gathering at next thematic group meeting | CARE with input from group members
Engage in dialogue with the private sector | EMW | Ongoing from April | EMW to identify opportunities for engaging the priviate sector, report back at regular thematic group meetings and coordinate related activities with input and support from group members | EMW | workshop already planned with PS to influence investment decisions and ensuring that these consider climate change impacts
Share information about private sector, donor and government interaction | All | April | EMW to collate information provided by group members at next thematic group meeting and share via email | EMW
Link NGO adaptation experiences to Government policy formulation processes to help set pro-poor priorities | CARE/C2C | April | CARE to coordinate identifcation of NGO adaptation messages (with input from group members) at next thematic group meeting; C2C to identify which policy areas these messages could influence. | CARE and C2C with input from all group members
Identify capacity among NGOs to engage with National Target Program and action planning processes of individual ministries | CARE | April | CARE to coordinate identifcation of NGO capacity (with input from group members) at next thematic group meeting and link with the policy thematic group to determine how NGOs can become involved in and feed NGO messages into national policy processes | CARE in input from all group members
Work with MARD on the Climate Change Adaptation Action Plan | C2C/CARE | Ongoing from April | C2C to determine from MARD whether any NGOs are or could work with the drafting committee and which areas need evidence from the field; provide case studies based on identified NGO adaptation messages | C2C with support from CARE and input from all group members | Resource person: Mr Ninh of CERED
support NGOs to mobilse local community voice and advocate with them at provincial and district level

## Acronyms
Acronyms
VGBC | Vietnam Green Building Council
EMW | East Meets West
C2C | Challenge to Change
CARE | Care International
NGO RC | VUFO-NGO Resource Centre
NDMP | National Disaster Mitigation Partnership
DMWG | Disaster Management Working Group
CCWG | Climate Change Working Group