Minute

Child right working group meeting

Participants:

- WV: Vu Thi Nga

- VUFO – NGORC: Phan Thu Ha

- ChildFund: Le Ngoc Bao

- VAPCR: Minh, Thao

- MACDI (Viện Tài chính vi mô và phát triển cộng đồng: Phương)

- MCC: Phúc

- Ô Xinh: Thủy

- CRS: Giang

- Plan: Hiển

- Chair: An - Plan

Time: 14.00- 16h30 Jan27th 2015

Venue: Plan office, 106 Hoàng Quốc Việt st.

Content:

| Content | Follow up action |
| --- | --- |
| Work plan for CRWG in 2015 Capacity building: Follow up the training plan which was agreed in the previous meeting. In deep, there will be several 1 day- training courses on child rights in basic, child participation, child protection and CR indicators in 2015. World Vision will conduct the first training in March. Sharing on specific themes integrated into periodic network meetings. Each sharing will last for about 1 hour including Q&A Advocacy: To prepare an Open Letter to Prime-Minister: Base on evidence on violence against children (could be from Child Helpline data or any other realizable data) to propose to the Government to have the next Child Protection Program from 2016 – 2020. This letter is needed to finalized and submit to the Prime Minister by April in the latest. Series of activities toward celebration of 25 years CRC implementation in Vietnam: We will wait for the detail plan of action from Children Bureau. Besides, CRWG will design a logo, this logo will be added in any activities relating to CRC. Support the provinces to make a plan of action on the following the recommendation of Concluding Observation from UNCRC and Degree 535 – Prime Minister. M&E: It is relating to indicators. Currently, there are many packs of indicators on child protection and care, however, they are not in line with each other. We need to have further discussions with Children Bureau about this issue. | Nga will send the TOR and training content to Ha NGORC for dissemination before Feb 10th. Each participated organizations shares at least 1 topic including tentative time for consolidation. CRS has registered for sharing on Disability Inclusion in May. Time will be confirmed later. Hà (NGORC) will consult with PACCOM and Marko for advice. An will draft an email in English by Feb 10th to all relevant organizations to seek the agreement and support. Anh Bảo (CF) works with Communication Dept to see if they can support in logo design or not. Each organization will send at least one idea for the logo by Feb 28th. An will design a form for organizations to list out all activities relating to the CRC. All organization will be requested to fill up by quarterly. Based on budget and working areas, each organization will decide to support at the provincial level not national level. VAPCR and CRS will work together to involve in this subject. |
| Nga – World Vision shared about Children Bureau’s work plan in 2015 Children Bureau would like NGOs to support them to conduct the Impact assessment and gender integration in the draft law. Consultation workshop will be conducted before submitting to the Ministries and National Assembly ( by end of April and May). Children Bureau has been collaborating with UNICEF to conduct the evaluation of the current National program on child protection and develop a continuous program. Indicator sets: Children Bureau has collaborated with UNICEF to organize a consultation workshop in Danang for indicators set on child protection. It is estimated that the national program on promoting child participation will be approved in next couple of months. Children Bureau has a plan to organize a press conference, competitions on website, photo voice… in order to celebrate the 25th years implementing the CRC in Vietnam. Cục sẽ gửi chương trình sớm cho các NGO để phối hợp Children Bureau would like CRWG to support provinces in develop plan of action to follow up the concluding observations. Theme of children forum this year is not finalized yet, bit it is more likely to link with child participation. Children Bureau is implementing the project on online database about child protection and care. This has been rolled out in some communes. | We will wait for the fourth drat by after Tet for further discussion. Plan will ask Children Bureau for the evaluation tools as well the new program framework for the 2016 – 2020. |
| Next CRWG meeting will be on March 19th 2015 at Plan office. |  |