## Summary
SUMMARY
Personnel cost | #REF!
Equipment cost | #REF!
Sub-contracting cost (*) | #REF!
Consumable&goods costs | #REF!
Other cost | #REF!
Sub Total | #REF! | Cross check | #REF!
Indirect cost (max 7%) | #REF!
Total cost | #REF!
(*) Sub-contracting cost
this is the evaluation cost only which I don't know whether it will be reckoned as sub-contracting. The costs related to construction activities (result 4) not included. They are part of activities and placed under "Other cost". If required, we can separate them.

## 2015 DMWG Action Plan
DMWG 2015 workplan - Outputs and Actions forward for 2015
No. | Tasks / Activities | Funding | Lead Agency(ies) | Collaborating agencies | Contact persons and emails | Dates |  | Status/Comments | Outputs | Indicators | Supporting docs / Sources of verification | Actions forward for 2015
[6 empty] | Planned | Executed
1 | Coordination in disaster management (CBDRM/ DRR)
1.1 | Lessons learned and best practices to support the rolling out of the National CBDRM program in upland areas- A contributing study to the 2015 midterm review of the National CBDRM program. | JANI | CARE |  | hieu.lx@care.org.vn | 2015-04-01 | 2015-08-01
1.2 | JANI meetings (to be debriefed at monthly DMWG meetings) | JANI | CARE/JANI members
1.3 | Mapping of CBDRM projects and programs | SCDM II | DMC | CCWG |  | 2014 | [5 empty] | On going
1.4 | DRR Portal (Vietnam) |  | DMC/ADPC | CARE
1.5 | Regional CBDRR Platform (relating to post-HFA) | SCDM II | UNDRMT | DMWG/CCWG | Jenty.Kirsch-wood@undp.org | 2015 | 2015
1.6
2 | Capacity building on DRM/CBDRM
2.1 | Training national and local master trainers in education sector (including the Ministry of Education and training, local departments of Education and Training) and documentation of the implementation process of the MOET action plan from national to local level | JANI | L&L |  | nguyet.dovan@livelearn.org | 2014-06-01 | 2015-09-01
2.2 | E-learning training package for sub national level to increase impact and coverage of current trainings related to the National CBDRM program. | JANI | PLAN |  | ninh.nguyentrong@plan-international.org | TBC
2.3 | On the job training for DMC staff in area where NGOs are implementing CBDRM activities | JANI | CARE |  | hieu.lx@care.org.vn | 2014-07-01 | 2015-08-01
2.4 | Support additional building blocks (Guideline and training package for national/provincial trainers) on climate and Disaster Risk Communication (CARE) | JANI | CARE |  | hieu.lx@care.org.vn | 2014-05-01 | 2015-08-01
2.5
3 | Advocacy and Policy Dialogue (DRR/CCA/ Emergency Response)
3.1 | International and National DRR days | JANI | SAVE |  | nguyenvan.gia@savethechildren.org | Oct 2014 & May 2015
3.2 | National Platform on DRR.CCA | SCDM II | UNDRMT | DMWG/CCWG | Jenty.Kirsch-wood@undp.org | 2015
3.3 | Quality and Accountability of humanitarian response (by (i)NGOs and Government, private sectors, etc.) |  | Sphere WG | Oxfam, WSPA, UNICEF, SC, etc.
3.4 | Follow up the materialization of DRM Law (Decrees, Resolutions, Circular, etc.) | SCDM II | UNDRMT | DMWG/CCWG | Jenty.Kirsch-wood@undp.org | 2015
3.5
4 | Coordinated emergency preparedness and response
4.1 | Relief Support Matrix | N/A | UNDRMT/ DMWG Chair | DMWG | [7 empty] | On going
4.2 | Emergency Meetings | N/A | DMWG Chair | DMWG
4.3 | Review/ renew JAT registration | N/A | Chair | DMWG
4.4 | JAT trainings and Simulation |  | ??? | DMWG
4.5

## Chair & Secretary Role 2008-15
Update list of DMWG Chairmanship for 2008-2015
Core Members | 2016 |  |  |  | 2017
| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
UN-DRMT
Oxfam
CARE
ActionAid
Plan
Habitat for Humanity
Malteser Int'l
World Vision
IFRC
Save
Core Members | 2014 |  |  |  | 2015
| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
UN-DRMT
Oxfam
CARE
ActionAid
Plan
Habitat for Humanity
Malteser Int'l
World Vision
IFRC
Save
LEGEND:
Chair role
Eligible to chair
Core Members | 2012 |  |  |  | 2013
| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
UN-DRMT
Oxfam
CARE
ActionAid
Plan
Habitat for Humanity
Malteser Int'l
World Vision
IFRC
Save
Core Members | 2010 |  |  |  | 2011
| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
UN-DRMT
Oxfam
CARE
ActionAid
Plan
Habitat for Humanity
ADRA
World Vision
IFRC
Save
Core Members | 2008 |  |  |  | 2009
| Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
UN-DRMT
Oxfam
CARE
ActionAid
Plan
Habitat for Humanity
ADPC
World Vision
IFRC
Save