Annex B: Terms of Reference

CARE International in Vietnam

TERMS OF REFERENCE FOR CONSULTANT

Project Title: 	Strengthening Civil Society Organizations’ to Curb HIV Infection among and Improve Care and Support for the Most Vulnerable Population Groups- Global Fund Against TB, Malaria and HIV/AIDS- Round 9, Track 2- (hereafter GF9).

Location:        	Hanoi

Duration: 		Around 50 days

Consultancy:		Modify existing Prevention Training framework curriculum

CARE International in Vietnam is a Non-Government Organization representing the CARE International network in Vietnam since 1989. CARE in Vietnam’s Program Strategy is explicitly oriented around achieving impacts for particularly vulnerable and marginalised groups in Vietnam. To achieve this, we work with Vietnamese partners across sectors such as health services, rural livelihood development, disaster risk reduction and climate change adaptation. We recognise that women’s empowerment is a critical pathway for poverty reduction and place women and girls from marginalised population groups at the heart of our programming efforts.

About Project:

The GF9 project is a consortium of organisations funded by GFATM and collaborating to strengthen the contribution of civil society to Vietnam’s response to the HIV/AIDS epidemic. Vietnam Union of Science and Technology Associations (VUSTA) is the prime recipient; Institute for Social Development Studies (ISDS), Centre for Community Health and Education (COHED) and Pact are sub-recipients while CARE is a sub-sub-recipient positioned within the program to provide technical and practical support to community based groups (CBO) during implementation. The project is designed as a five year project linked to and complimenting the GFATM Round 8 project being currently being implemented by the GoVN.

The GF9 project Track 2 will work in 10 provinces to compliment and extend the national HIV/AIDS programme by engaging CBOs in HIV/AIDS prevention and care activities, strengthening their organisational and technical capacity, providing an avenue for funds to reach the community sector by facilitating an HIV/AIDS sub-grant program for civil society.

IDU, SW, MSM and PSP have been identified as the most vulnerable populations for HIV infection in Vietnam.  Although HIV prevention and care services have made significant advances in quality and coverage for the general population, the coverage of essential services for these populations remains low. The assumption underlying this project is that lower service coverage for these populations within the national response is, in part, a result of lower participation of individuals and groups in service design and delivery. This project hopes to increase service access and choices for key populations, strengthen and link emerging civil society groups in Vietnam to mainstream services, and assisting the government in their efforts to extend HIV/AIDS programming to the most vulnerable.

Project Aims and Objectives

The project aims to make a breakthrough in civil society’s engagement in realization of the national strategy on HIV/AIDS by actively collaborating with and complementing the government’s response to HIV through the GF8 to reduce HIV transmission among sex workers (SW), men-who-have-with-men (MSM), injecting drug users (IDU) and their primary sexual partners (PSP) and improve care and support for members of these populations who are living with HIV.

The specific objectives include:

- Provide care services and comprehensive supports for OVC and PLWH in the communities

- Provide mitigation services to reduce HIV infection rates among IDUs and female sex workers in one province, among MSM, IDU and sexual partners of the PLWH.

- Creating a favourable environment for the growth and participation of civil society in dealing with HIV/AIDS

- Strengthen capacity of CSOs to optimize their contribution into HIV/AIDS pandemic confrontation.

Key project activities

- Raise awareness on rights and needs of IDU, sex workers, MSM, PSP and PLHIV and reduce stigma and discrimination against these populations.

- Support the establishment of support groups for the target populations.

- Build capacity of civil society organisations to deliver services or support service delivery.

- Create communication channels and foster dialogues between targeted populations and intervention designers and implementers.

- Implement evidence based interventions for targeted populations in the community and closed  settings

- Foster mutual learning and collaboration among stakeholders at all levels.

Proposed Consultancy

In order to support quality and consistency of prevention and care services being delivered by CBO and to ensure that these services comply with and compliment GoVN standards, a range of technical guides will be developed to support implementation. This consultancy focuses on approaches to HIV prevention and will result in the development of a prevention training package (guided by existing Prevention Frameworks for each of the target populations which have already been developed by Pact as part of this project)

Scope of Work:

- Modify existing prevention training packages to be used by participating CBOs during implementation of the GF9 project. The package including 10 module:

Pending approval of an agreed work plan, the consultant will:

Modify existing prevention training framework curriculum to be used by participating CBOs during implementation of the GF9 project.

- Develop detail plan.

- Discuss with ISDS, COHED, PACT and selected CBOs to learn their expectations.

- Review existing prevention training material

- Finalize Prevention training framework curriculum

Expected Outputs

- Work plan, including schedule and budget, agreed by CARE.

- Detail consultation plan

- Finalize prevention Training framework curriculum

Tentative Work Plan

| Task | No of days | Due dates |
| --- | --- | --- |
| Review Pact’s Prevention Frameworks, existing prevention training framework curriculum and other documents (existing FHI, including those of CBO implementing partners, GVN and other INGOs.) | 4 |  |
| Discuss with ISDS, COHED and PACT to focus of priority activities of GF project | 1 |  |
| Prepare first draft base on the prevention training framework curriculum ISDS, COHED and PACT for comments | 20 |  |
| Consultation with ISDS, COHED and PACT | 1 |  |
| Finalize the prevention training frame curriculum | 24 |  |
| Total Days | 50 |  |

Selections criteria / qualifications requirement for the consultant

The prospective consultant will require an appropriate balance of training facilitation skills and experience working with PLHIV as well as good communication and strong interpersonal skills.

Qualifications should include:

- Master of Public Health or equivalent.

- At least 5 years’ professional experience, preferably in HIV project

- Excellence in writing HIV prevention training curriculum

- Significant understanding and application of active and participatory method into training.

- Significant track record in conducting and facilitating training workshops, especially with PLHIV of CBOs.

COMPLETION DATE FOR ALL ACTIVIITES:  30 Oct 2013

Interested people should send CV and cover letter to Procurement@care.org.vn, deadline for application is 30 August 2013. No telephone contact please.

# Text boxes

Basic knowledge and skill

Module 1: General of outreach community

Module 2: STIs and HIV basic knowledge

Module 3: Behaviour Change Communication

Module 4: Sexual and sexual health

Module 5: Reproductive health

Module 6: Basic knowledge of drug, addiction

Typical knowledge and skills for prevention individual target group

Module 1: Prevention for Injection Drug Users (IDU)

Module 2: Prevention for men who have sex with men (MSM)

Module 3: Prevention for principal sexual partners of injection drug users and people living with HIV (PSP)

Module 4: Prevention for Female Sex Workers (FSW)