SCOPE OF WORK

Content in website and online support under REACH 4.0 modality in Hanoi

I. Background

HIV prevalence among men who have sex with men (MSM) in Hanoi remains high at 4-6% from 2011-2016 (HIV Sentinel Surveillance HSS+). Notably, results from a recent study by the Hanoi Medical University in 2017 show that HIV prevalence among MSM can be up to 10.9%. The Vietnam Administration for HIV/AIDS Control (VAAC) estimates that 30,147 MSM lived in Hanoi in 2017. Among those, only about 11,600 can be reached by traditional outreach approaches. An investigation of HIV positive testing sample of MSM from July 1 to December 30, 2017 in Hanoi’s voluntary counselling and testing centers (VCTs) by CDC shows that 35.7% were recently infected within six months, suggesting that there may be a potential HIV outbreak among MSM in the city.

Based on the assessment of the implementation of enhanced outreach approaches (EOA), Fanpages and other MSM communities in Hanoi, USAID SHIFT project will lead and coordinate technical activities to develop and introduce the REACH 4.0 strategy for HIV prevention and treatment retention programming among MSM and LGBT communities in the next phase.

REACH 4.0 is an innovative outreach method that combines key population (KP)-led outreach approaches and assisted or facilitated service delivery models with technology use of BIG DATA in reaching, promoting, linking and following up targeted high risk and hidden MSM and LGBT throughout the harm reduction and HIV/AIDS cascade. Beside virtual size estimation and intensified case finding, REACH 4.0 enables a real-time data entry, reporting and analysis for a dynamic program management and community-based outreach finance transition solutions (O2O modality, web-based/online order & provision of STIs/HIV testing as well as PreP/PEP and ARV treatment retention by CBS).

Under the workplan of COP17, USAID SHIFT has piloted the REACH 4.0 modality in Ho Chi Minh City. The project needs to hire an outsourcing partner to expand the model in Hanoi.

II. Deliverables:

USAID SHIFT expects the selected outsourcing partner to provide the following services:

- To design website interface. Technical requirement must include but not limit to:

  - A new interface with a tab of REACH 4.0 modality run on Hanoi Preventive Medicine Center (PMC) official website www.ytdphanoi.gov.vn;  and G-Town’s website: http://gtown.vn/

  - Visualization of “Reach 4.0” tab: Friendly, eye-catching and colorful interface to MSM;

  - Content developed in consultation with MSM advisory team members and USAID SHIFT staff order to pull and engage MSM users in Hanoi to access, online self-assessment and use the O2O service modality.

- To manage REACH 4.0 contents displayed on the cover-page in a separate headline tab in the following orders:

  - HIV monthly updates (news highlights, photos and videos)

  - Testing services: Lay testing, Oral quick, HIV testing and counselling (HTC) sites as in friendly service promotion model;

  - Treatment services: PreEP, HIV treatment facilities (HTFs/OPC) as in friendly service promotion model;

  - Links to G-Town’s website (http://gtown.vn/) and other Fan-pages of MSM communities

  - Other materials as required;

Note: Proposed themes for other materials: (1) Risk behaviors and HTC promotion; (2) HIV-related supporting services for KPs.

- Create the chat box on interface with REACH 4.0 run on G-Town

III. Time-line

| Activities | Deliverables | Due Date (tentative) |
| --- | --- | --- |
| - Reach 4.0 tab concept development | Concept developed | June 8, 2018 |
| - Design website interface | First draft of interface with REACH 4.0 run on Hanoi PMC and G-Town’s websites | June 15, 2018 |
| - Design website interface | Final interface with REACH 4.0 run on Hanoi PMC and G-Town’s websites | June 20, 2018 |

SUBMISSION DEADLINE

May 25th, 2018 to myhanh@fhi360.org