SCOPE OF WORK

Promote HIV testing among key populations

I. BACKGROUND

USAID SHIFT is working with the Government of Vietnam and select community partners to accelerate HIV epidemic control. This includes helping increase the number of people living with HIV (PLHIV) who are aware of their HIV status. To do so, the project and its local partners seek to increase key populations’ (KP) awareness and uptake of HIV testing services. These KPs include sex workers, their clients and partners; men who have sex with men (MSM) and transgender people (TG) and their partners; and people who formerly or currently inject drugs (PWIDs) and their partners.

II. REQUIREMENTS

USAID SHIFT seeks support from a forward-thinking, KP-sensitive firm to help design and disseminate a targeted campaign to promote HIV testing among highest risk populations. The selected vendor must:

- Be highly sensitive to the full spectrum of key populations at risk for HIV in Vietnam

- Craft messages which resonate with target audiences in a positive and productive way, without reinforcing stigma or fear related to HIV

- Produce content which can be readily disseminated on a variety of platforms, including social media, online dating and hookup applications, and potentially in print

- Design content which targets specific demographic groups, including low-income KPs based in and around Hanoi, and KPs based in the Ho Chi Minh City metropolitan area

- Be ready and willing to adapt content to client feedback and needs

- Produce all content in both English (for client review and approval) and Vietnamese (for dissemination)

- Produce a total of _15_ pieces of content, comprised of still images, GIFs, and/or short video clips (ex: 6 still images, 6 GIFs, and 3x 30 second videos)

- Help measure target audiences’ exposure and response to the campaign

III. DELIVERABLES

A schedule of deliverables is provided below.

| No. | Deliverable | Due Date |
| --- | --- | --- |
|  | Outline of proposed content, dissemination strategy, timeline, and metrics | December 10 |
|  | First five pieces of content (still images, GIFs, and/or short video clips) finalized | December 25 |
|  | Second five pieces of content (still images, GIFs, and/or short video clips) finalized | January 20 |
|  | Third five pieces of content (still images, GIFs and/or short video clips) finalized | February 20 |