# SCOPE OF WORK

# Consultancy for Global Fund, Pact sub-project under VUSTA component

# December 9, 2011 to January 31, 2012

- Background

The Global Fund to Fight AIDS, Tuberculosis and Malaria was established in 2003 to support countries all over the world in response to these 3 century epidemics. Vietnam has recently received funding under Round 9 with a proposal entitled “Government – Civil Society partnership in responding to HIV epidemic in Viet Nam and moving towards Universal Access and sustainable National AIDS program”. Under this project both government and civil society will receive funding.

Pact is a member of the civil society consortium under this project and takes the lead role in technical and organizational capacity building of participating Vietnamese NGOs. This will be done by developing and applying diagnostic tools to identify organizational needs and gaps, developing and providing high quality training packages and providing technical and organizational mentoring support and follow-up. In the initial phase of implementation, these NGOs are COHED, CHP, LIFE, ISDS, and VICOMC who will support CBOs in their HIV prevention programs with men who have sex with men (MSM), female sex workers (FSWs), injecting drug users (IDUs), primary sex partners of people living with HIV/AIDS and IDUs (PSP). The current project sites are in 10 provinces including Hanoi, Hai Duong, Vinh Phuc, Vinh Long, Can Tho, Bac Kan, Nghe An, Ho Chi Minh city, Binh Duong and Vung Tau.

The purposes of this consultancy are

- To assist Pact’s team in provision on-site mentoring support to VNGOs to monitor progress and provide technical assistance as needed on prevention interventions with MSM, FSWs, IDUs and PSP in 3 project provinces.

- To assist Pact’s team in development of hand-out material on PSP program which will be integrated into peer education training package.

- Scope of Work

Pact is seeking 02 consultants to assist Pact’s team to fulfill the two mentioned purposes. The consultancy period is from December 5, 2011 to January 31, 2012. Breakdown of tasks is anticipated to be as follows:

For mentoring support:

| No | Tasks | No. of days |
| --- | --- | --- |
| 1 | To work with Pact prevention team to review Global Fund intervention frameworks, VNGOs workplan and Pact training materials, mentoring guideline for field work plan and preparation (second week of Dec) | 2 |
| 2 | To conduct field work in three provinces and provide on-site mentoring support to VNGOs to monitor progress and provide technical assistance as needed (second and third week of Dec) | 6 |
| 3 | To prepare reports of the field work with specific recommendations for follow-up technical support to the visited VNGOs (fourth week of Dec 2011 and first week of January 2012) | 4 |
|  | TOTAL | 12 |

For development of hand-out material:

| No | Tasks | No. of days |
| --- | --- | --- |
| 1 | To review Global Fund intervention framework and Pact training materials as well as current PSP models carried out in Vietnam (second week of Dec) | 2 |
| 2 | To develop an outline of the materials in Vietnamese and work with Pact for final agreement (second week of Dec) | 2 |
| 3 | To develop the hand-out material in Vietnamese based on the agreed outline (third week of Dec) | 5 |
|  | TOTAL | 9 |

The consultant rate will be discussed and agreed between Pact and the consultant on the basis of the project’s policies and qualification of the consultant. Deadline for application is December 9, 2011 COB.

- Report

The consultant will work with Prevention team and the Coordinator of Global Fund program in Pact. The consultant will report to the Prevention Program Officer who is in charge of this activity.

- Desired qualifications, skills and qualities:

- At least 5 years’ experience in HIV/AIDS programming

- Experience with the following:

  - Prevention program with at most-at-risk groups (CSWs, IDUs, PSP,  and MSM): BCC and Prevention outreach

  - Practical experience in working with VNGOs and CBOs in HIV programs

  - Global Fund project context

  - Community mobilization

  - Program planning, implementation, monitoring and evaluation

  - Working in an international NGO context a plus

  - Mentoring and building partnerships with local organizations and CBOs

- Good training and facilitation skills

- Advanced spoken and written English; fluent Vietnamese