TERMS OF REFERENCE

Job title:	Short-term consultancy for assessing village rice yield in Winter-Spring 2012/2013 crop

Reports to:	CCA Programme leader

Supervisor:	Project Coordinator/Livelihood Advisor

Duty Station:	Nghi Loc district / Nghe An Province

- Background:

The Netherlands Development Organization (SNV Vietnam) is currently implementing a project titled “Innovative financing for building community resilience to climate change in coastal Vietnam”. Agriculture Community Based Insurance (Agri.CBI) is one of four components of the project. The project is implementing in 5 communes: Nghi Cong Nam, Nghi Lam, Nghi Thai, Nghi Van and Nghi Yen of Nghi Loc district, Nghe An province.

The Agri.CBI to rice cultivation is piloted in the Winter-Spring 2012-2013 rice crop at village level of those five communes. Currently, paddy rice is in grain filling and ripening stages. Rice harvesting is expected to be started in soon in May. Under the context of the Agri.CBI pilot, SNV is looking for a Local Consultant  to undertake Rice Yield Assessment at village and commune level. The final results of yield assessment are used to calculate yield loss of insured rice area and villages.

- Objective:

Actual village rice yield is assessed and certified for local authorities and related stakeholders use the results of assessment to calculate yield loss of the Agri.CBI pilot villages in the Winter-Spring 2012/2013 crop.

- Scope of work:

The Consultant will undertake an assessment of actual rice yield of 51 villages in the 4 communes for the Winter–Spring rice crop 2013, of which 11 villages in Nghi Thai, 17 villages in Nghi Van, 17 villages in Nghi Lam and 6 villages in Nghi Cong Nam commune, Nghi Loc district.

In order to conduct actual rice yield assessment, the consultant will take 6 harvesting samples in each village (2 samples from fallen rice field caused by recent Tornado, 2 from good and 2 from average paddy field) 306 samples will be taken from 51 villages in total. In addition, he/she will interview 510 households (10 households per village) to obtain post- harvest rice yield of farmers.

The consultant will assist to present result of assessment and  certification and documentation of final assessment results.

- Tasks:

- Work closely with Project coordinator and project consultants to develop a detailed work-plan including field working plan to get samples, household interview and data assessment

- Prepare appropriate methodologies for selecting assessment samples and calculation of  actual rice yield at village level.

- Assist village, commune, district and involved actors in CBI to do selection  samples for harvesting assessment of paddy field, calculate theory and actual rice yield

- Interview farmers to post harvest rice yield with support of project team

- Calculate and consolidate final average rice yield from theory rice yield and actual rice yield

- Facilitate with certification of average rice yield of CBI 51 villages with signatures and stamps of the District Statistic Bureau

- Submit results of rice yield assessment in timely manner.

- Deliverables:

- Work-plan is submitted to SNV within 5 days, before further work undertaken

- Data of calculated actual rice yield of Winter-Spring 2012/2013 crop of every of each 51 villages in 4 communes is assessed accurately and certified by the District Statistic Bureau

- The results of rice yield assessment are submitted to SNV and the 4 communes in time.

- Final mission report

- Cost proposal:

- Maximum duration is 23 person-days, suggested as follows:

| No | Description | Number of man/day |
| --- | --- | --- |
| 1 | Desk study - to understand project and CBI in particular | 2 |
| 2 | Instruct project team and commune staff methods of getting samples and calculate actual rice yield: | 1 day |
| 3 | Identify and implement selected samples harvesting in paddy fields and calculate theory yield in CBI village and communes | 10 days |
| 4 | Interview farmers to obtain post harvest yield data (supported by project team): | 5 days |
|  | Consolidate and calculate final actual average yield at village and commune level for each village and commune in CBI communes. | 5 |

Assignment location: Village of Nghi Thai, Nghi Lam, Nghi Van and Nghi Cong Nam communes, Nghi Loc district, Nghe An province.

- Timeframe:

- The detailed workplan should be submitted to SNV before 11th May, 2013.

- Instruct project team and commune staff methods of getting samples and calculate actual rice yield before 02th May, 2013

- Harvesting samples and households interview should be conducted before 15th May, 2013

- The result of rice yield assessment will be submitted to SNV and the 4 communes not later than 30th June, 2013.

- Consultant qualifications:

- At least Bachelor degree in Agricultural, Statistic and relevant field

- Good analytical and statistic skills

- Proven experience in  rice yield assessment

- Participatory and community based working approach

- Proven experience in working with district, commune and village authorities.

- How to apply

Interested applicants are invited to submit : 1) full CV ; a short proposal stating appropriate technical approaches and remuneration package to Mr. Manh Loc Khoa, Project Coordinator at KManhLoc@snvworld.org with c.c to ATranTu@snvworld.org. Deadline for application is 5.pm of 10th May,2013.