

Green Bamboo project

____________________________________________________

Terms of Reference for the final evaluation

Patricia Toelen

Phuc Van Nguyen

Aurélie Vogel

septembre 2013

RSE

Campus du Jardin tropical

45 bis avenue de la Belle Gabrielle

94736 Nogent-sur-Marne Cedex, France

Tél. : 33 (0)1 70 91 92 00

Fax : 33 (0)1 70 91 92 01

gret@gret.org - http://www.gret.org

Terms of Reference

- FINAL EVALUATION OF THE PROJECT

- ----------------------------

# Background

GRET is a French non-profit association that has been actively fighting poverty and inequalities for 35 years. Its professionals provide lasting, innovative solutions for fair development in the field and work to positively influence policy. Active in more than 30 countries, GRET has 13 permanent branch offices in Asia, Africa and Latin America. In Vietnam, Gret permanent presence started in 1989 with the creation of a Vietnamese-French bilateral cooperation program together with the Vietnam Agriculture Scientific Institute (VASI). Gret's  strategic intervention focus on Sustainable Natural Resource Management; Livelihoods Development; Bamboo Production and Commodity Chain; Renewable Energies; Climate Change Mitigation and Adaptation.

The project “Green Resources, Environment and Innovative Small Enterprises in the Bamboo Commodity Chain – Green Bamboo” funded by French Development Agency (AFD) has been implemented in 5 districts of Western region of Thanh Hoa province i.e. Quan Hoa, Ba Thuoc, Ngoc Lac, Thuong Xuan and Lang Chanh. This is the largest area of bamboo plantation forest of Vietnam. The Green Bamboo project started in 2010 and will be completed by the end of October, 2013.

Project aim

To promote socio-economic development in the region and contribute to climate change mitigation through sustainable management and improvement of environmental and economic values of bamboo forest resources

Specific objectives

To develop local adapted livelihoods and small businesses in the bamboo sector and a set of references on carbon impact and environmental services, so as to increase revenues and local added value for producers while protecting the environment of the North West Thanh Hoa region.

Project Outcomes

- Local bamboo-processing small businesses will develop and diversify their production due to access to financial and non-financial services

- Plantation management improved and climate change mitigation measures tested through enhanced carbon emissions reduction and innovative energy efficiency solutions

- Structural improvements in the sector which encourage exchanges and agreements among professionals, helping to steer the sector, and consultation with state actors with a view to building an institutional environment that promotes sector development

Project strategic intervention

- Improving bamboo management practices and local livelihoods among local producers, to ensure more effective and sustainable management, helping to assist climate change mitigation by exploring opportunities for setting up projects such as Carbon compensation mechanisms ;

- Supporting the creation and development of local bamboo processing small and medium enterprises (local added value), through advisory and support, training (management, processes and products, sale and distribution, quality issues, access to markets …), and access to credit;

- Promoting better business structures and support services to farmers, consultation among different stakeholders and with state authorities, policies favoring professional organizations, associations, setting up an observatory of the sector, with capitalization on knowledge and lessons learned.

# Objectives, content AND METHODOLOGY of consultancy

## General objectives

- To evaluate the performance of the project

- To determine strategic interventions and make recommendations for future development of the bamboo sector in the region

Specific questions :The evaluation will address the entire project implementation cycle, its outputs, outcomes and impacts on the bamboo commodity sector of Thanh Hoa province.

The consultant will analyze the development of the project from the appraisal phase till the evaluation. He will report the project development and the difficulties/events occurring during the project.

The consultant shall evaluate the performance of the project using the five criteria recommended by the OECD DAC: relevance, effectiveness, efficiency, impact and sustainability.

### Relevance :

Relevance examines: (1) the consistency of the intervention with respect to the objectives and issues determined at the outset; (2) the internal consistency of the project to achieve the objectives; (3) the external consistency of the project with other interventions.

More specifically:

- Do the project general and specific objectives respond to the problems identified in the bamboo sector in Thanh Hoa at the beginning of the project?

- - The increasing pressure on bamboo resources due to over-harvesting or harvesting of young bamboo shoots;

- - The fragility of local small workshops (cash flow difficulties, low rate of valorization of bamboo products…)

- - The low added value created locally from bamboo supply chain in view of the ?

- - The lack of enforcement and support of small producers and workshops from government

- Has the bamboo sector evolved during project duration and if yes, how did the consistency evolve over time?

- Are the project’s intended target groups the actual beneficiaries of the project?

- Was the project in line with other national policies, strategies or interventions of other stakeholders?

- Was it relevant to work in priority with local actors (CRD, association of bamboo entrepreneurs, bamboo producers groups)?

### Effectiveness

Effectiveness assesses the extent to which the project’s objectives were fulfilled, as well as its possible unexpected effects (positive or negative effects). It includes: (1) a comparison of intended and actual project results; (2) an analysis of the gaps observed.

- Were outputs achieved for each of the 3 components and to what extent?

- Do the intended beneficiaries all have access to the results and services produced by the project?

- How did the project take into account gender equity in its methodology, and how is this reflected in the results obtained?

- Any other output that was not planned by the project?

- Based on the analysis of project’s outputs, were the objectives of the three components achieved and to what extent?

More specifically:

- Did the project’s support allow local workshops to develop new technologies and products and to reach and sustain new market opportunities? If not, what are the remaining gaps?

- Did the project’s support allow improving the soundness of local workshops thanks to a better access to financial and non-financial services?

- Did the project manage to promote innovations to solve the problem of pollution from the production of paper pulp?

- ow HowWho is currently using the referential for sustainable management and rehabilitation of bamboo forests, and for which purpose? Could the diffusion and promotion be improved? How?

- Did the livelihoods fund allow reducing the financial pressure on bamboo plantation of poor smallholders? What could have been the other leverage used to reduce this pressure? Are there other sources of pressure on bamboo plantations?

- What are the results of the prospective work on other sources of financing for the sustainable management of bamboo forests?

- Did the project support manage to structure the bamboo supply-chain and to facilitate the dialogue and consulting among stakeholders? Did it contribute to improve the institutional environment for the development of the local supply-chain?

- What is the quality of the data and information provided by the observatory of the bambo supply-chain and market? Who is using these data? And for which purpose? Could the diffusion and promotion be improved? How?

### Efficiency

Efficiency examines the relationship between the resources implemented and their costs, on the one hand, and the funded outcomes, on the other hand. This will involve assessing whether the resources of the project (funds, expertise, time, etc.) have been converted into results in an economical manner.

- Were the required resources made available in a timely manner and at the budgeted cost?

- Were the financial, technical and human resources implemented in a timely fashion and at the least cost ?

- Were the activities carried out as planned?

- Were the activities regularly and adequately monitored, and were corrective measures taken if needed?

- Carry out a benefit-cost analysis of the resources of the project versus results obtained.

- Does the analysis show any excessive delay or overspread?

### Impact

Impact measures the benefits of the intervention. The consultant assesses the impact on: (i) bamboo-processing small businesses (ii) the bamboo plantations, (iii) the bamboo sector of Thanh Hoa.

- Did the project contribute to increase the added value created by the bamboo value chain? If yes, is this added value well distributed between stakeholders? Is there any effect on the sustainability of the bamboo plantations?

- Did the benefits of the bamboo enterprises increase?

- Did the households’ income increase? If yes, is this increase available in cash? Is there specifically an impact on the poorest?

- Can the impacts be measured according to the different groups of beneficiaries targeted, and in particular in terms of gender equity?

- What were the project’s impacts on the environment/management of natural resources?

- Were there any negative/unexpected impacts of the project, and did the project propose any mitigation measure?

- What is the impact on the long term for the strengthening of the civil society: CRD, Bamboo Enterprise Association, TxT? What is their strength?

### Sustainability

The consultant examines whether the results and impacts obtained are of a sustainable nature, or even likely to be amplified, over the long term, and, if so, under what conditions. The analysis covers the institutional, technical and financial sustainability.

- What are the long term benefits for the bamboo enterprises  /bamboo owners / bamboo plantations/bamboo association in terms of better practices, income, etc?

- How can the services provided by the project be maintained after its end, on a financial / technical / institutional point of view?

- Can the benefits of the project be sustained, should economic factors be subject to variability? (commodity prices, exchange rates, etc.)

- What is the likelihood that the target groups and beneficiaries will continue to use the services provided once external financing ends?

- To what extent the project has been supported by / has established linkages with the public and private sectors?

- Is the project embedded in local institutional structures that will continue after project completion? Are project partners sufficiently trained to take over the activities of the project (at a technical, financial and administrative level)?

### Capitalisation

The consultant shall also prepare a general conclusion, and lessons learned/ recommendations which can be both strategic and/ or operational for potential future interventions and development of the bamboo sector of Thanh Hoa province.

### Administrative and financial management

- Did the reporting to donor respect the convention requirements?

- Were the funds used in accordance with budget planning?

- Were the financial contributions gathered according to the initial financing plan?

## Methodology

### Literature review

The evaluation team should get acquainted with the existing project documentation:

- Project proposal document

- First and second annual project technical reports

- Periodical reports on project implementation progress and achievements

- All other relevant field reports and documents

### Field work

Fieldwork should be conducted through semi-structured interviews with key informants such as small bamboo producers, local bamboo processing entrepreneurs, field based project staff and local authorities. It is suggested that the following professional and social organizations should be examined: Bamboo Entrepreneurs’ Association (BEA), Farmer Organization/Group, Center for Rural Development (CRD).

## Key tasks of the consultancy

The consultants will be responsible for implementation of the following tasks:

- Develop a working approach, information/data collecting procedures, selection of key informant groups, field visit schedule and process.

- Review all necessary project documents, quarterly project activity implementation plans, field reports, training materials etc.

- Undertake an initial briefing with the project staff before the evaluation for obtaining staff inputs.

- Implement the agreed evaluation activities: Meet and interview with project staff, local partners and beneficiaries, field visit and observation…

- Analyze information and draft a preliminary evaluation report that includes results, impact, lessons learned and recommendations.

- Facilitate a workshop to gather feedback of project stakeholders on the outputs, findings and recommendations of the evaluation.

- Consolidate and finalize the evaluation report.

## Outputs of the evaluation

The consultants will produce a final Evaluation Report of maximum 25 pages (without Annexes) in good concise English including:

- Executive Summary with summary findings, lessons and recommendations.

- Analysis of project relevance, effectiveness, efficiency, impacts and sustainability of results – as described above .

- Analysis of lessons learned and general or specific recommendations for potential future interventions.

- Conclusions and recommendations.

- Annexes:

  - Methodology

  - TOR of evaluation

  - List of documents consulted

  - Itinerary and people met

  - Other relevant documents

The evaluation reports will be submitted in hard copy as well as in electronic form containing the text and tables in Microsoft Word and Microsoft Excel. The report will be written in English.

III   MODALITIES AND LOGISTICS

## Time schedule

The evaluation will be done in a maximum of 13 days, starting on 12st to 25th October, 2013.  The detailed schedule will  be agreed upon by all stakeholders.

Type of work				Working time

- Preparation:					2 days

- Fieldwork: 					5 days

- Preparation for feedback workshop: 	1 day

- Feedback workshop:				1 day

- Traveling HN-Quan Hoa- HN			1 day

- Report preparation:				3 days

Total working days	 			13 days

## Consultant team

The consultant team will include a team leader and 2 members with strong expertise in commodity value chain approach, sustainable natural resource management, participatory methodology, community based development.

- Details responsibility of consultant team

| # | Team members | Task/responsibility |
| --- | --- | --- |
| 1 | Expatriate Consultant – Team Leader (1) | - Overall supervision/coordination of consultancy - Methodology development and supervision - Participation in field work - Leading in data/information collection and analysis - Drafting of a report - Presentation of finding in a feedback workshop - Consolidate and write a final report |
| 2 | Team members – Local Consultants (2) | - Assist the team leader in coordination, planning and organization of field work - Contribution to data/information collection and analysis - Participation of field work and reporting |
| 3 | Field Based Project Coordinator (1) (Team member) | - Facilitation of field work - Making contact and appointments - Contribution to data/information collection and analysis - Providing feedback to a draft report |

## Logistics

Gret will provide transportation, office facilities and food/accommodation for the consultant team.

## Call for consultants

International and national consultants are invited to send expressions of interest through a cover letter presenting the consultant(s) with examples of past consultancies which demonstrate relevant capacity and experience for this evaluation. The consultants should also provide a detailed technical and financial prooosal, including :

- CV of proposed personnel

- Proposed methodology/suggested itinerary of the evaluation

- Expected number of consultancy working days  and work plan

- Consultancy budget, including fee rates and all other costs

The application should be received no later than 5 pm on 10th October 2013 to Ms Huynh Thi Diem Thuy at gretvn@gret.org.vn

Please note that all documents must be submitted in English and only short-listed candidates will be contacted.

### Contact person

Mr Nguyen Van Phuc, Manager of Green Bamboo Project

Tel: 04 38464493 - Mobile: 0912670674 - Email: phuc.smp135@gmail.com