TERMS OF REFERENCE

TITLE:	National Public Finance Specialist

PURPOSE:	To provide technical and coordination support to the international specialist in an assignment for the Committee on Finance and Budget Affairs of the National Assembly of Viet Nam. The assignment will focus on reviewing the draft State Budget Law and providing recommendations for amendments in view of the upcoming consideration of the draft law by the National Assembly and the respective Committee.

DURATION OF ASSIGNMENT:	Up to 30 working days(including during 3 missions of the international specialist) from December 2013 to October 2014

COUNTRY OF ASSIGNMENT:	Hanoi (with possible field trips to provinces)

- Background:

- Viet Nam, as a middle income country, is facing new challenges which require more efficient resource allocation and greater attention to rising disparities. Institutional reforms and sophisticated, responsive and accountable modern institutions are needed to manage these  challenges.  The Socio-Economic Development Strategy for 2011-2020 reaffirms that Viet Nam needs to continue to reform its policy development process and have stronger and more effective institutions, enhanced parliamentary law-making and oversight processes  and greater participation by all stakeholders and citizens in law and policy making, planning and monitoring. This will facilitate more equitable access to public services and help address rising disparities.  It will also contribute to a more inclusive and competitive economic growth trajectory.

- Vietnam has been accelerating public finance reform. Prime Minister’s Decision No. 450/QD-TTg (18 April 2012) on a finance strategy up to 2020 clearly indicates the necessity of building a healthy national finance system, guaranteeing to maintain financial, macroeconomic and monetary stability; creating conditions to promote economic growth associated with a growth model reform and economic restructuring; solving social-security problems; raising, managing, distributing and using the financial resources of the society effectively and fairly; and guaranteeing the effectiveness and efficiency of the financial management and oversight.

- At the center of the public finance reform is the revision of the State Budget Law. The current state budget law was approved by the National Assembly of Viet Nam in 2002 and has been implemented from the 2004 fiscal year. The law’s implementation over the past nine years revealed many shortcomings that prompted the government to initiate the process of amending the law. The ongoing constitutional amendment process also calls for amendment of the budget and other important/organic laws. A new draft budget law has been prepared by the government (with Ministry of Finance as the principle drafting body) and will be submitted for the first reading at the National Assembly (NA) session in May-June 2014.  The document is to be reviewed for the second time and approved at the NA session in Oct-Nov 2014.

- UNDP’s Project “Strengthening the capacity for budget oversight of elected bodies in Vietnam” is supporting the National Assembly’s Finance and Budget Committee to prepare for and review the draft law. Since early 2013, the project has organized a numbers of national and international conferences on state budget law amendment issues.   These workshops/conferences provided a good opportunity for Committee and other National Assembly Members to discuss with government officials, representatives of lower levels of government and national and international experts issues related to the upcoming law amendment process and the role of parliament in the process of budget review and oversight.  Some of the issues discussed in connection with the revision of the budget law revolve around:  integration of budget management; medium term fiscal and medium term expenditure frameworks; output-based budgeting approach, decentralization of spending duties; parliamentary review and oversight of state budget; accountability of line ministries;  information flow, reporting, budget disclosure; equity issues relating to the budget law process, and transparency.

- To further support the CFBA in reviewing and improving the draft budget law UNDP seeks the engagement of an international public finance specialist and a national public finance specialist.  The national specialist is expected to support the international specialist to analyse the existing budget law and proposed revisions with a view to provide recommendations for improving provisions relating to enhancing participation, transparency, accountability and parliamentary oversight to, among others, ensure a more equitable and inclusive budget process and resource allocation.

- Analysis and recommendations will be complemented by evidence from field work. This field work will be conducted by local researchers and/ or CSOs. CSOs will also be engaged to support the overall consultation and advocacy process.  The national public finance specialist is expected to support the coordination of the field work as well as provide inputs from local perspective to the international specialist’s overall guidance to the field work preparations, implementation and analysis of findings.

- The national specialist will also ensure the availability of updated and accurate translations of the various drafts of revised budget law.

- Scope of Work and SPECIFIC TASKS:

Under the supervision of National Project Director (NPD), the UNDP Governance Unit Head and the international specialist, the national public finance specialist is expected to support the following tasks of the international specialist through collecting and providing accurate and timely information, facilitating stakeholder communication, providing coordination support (particularly during international specialist’s missions to Viet Nam), and offering substantial inputs and technical assistance from a local perspective:

- Analysis of the current budget law (as well as various available drafts of the revised budget law) and identification of gaps in  light of international standards and good practices on transparency, participation, accountability as well as from an equity perspective.

- Review of Oxfam Great Britain - led NGOs’ proposed workplan supporting the revision process of the law and providing leadership/advice in the conceptualization of a field work process with participation of these NGOs to complement the development of policy notes.The national specialist will support the international specialist in working with Oxfam GB and the NGOs to agree on a concept note and a TOR for the field work - including key issues on which the public should be consulted and a detailed field work plan.

- Development of various policy notes and a summary note based on the above analysis and field work that provide recommendations for amendments of the proposed revised budget law. These notes will include the following:

- Principles of accountability, transparency, participation and equity in public finance and budget management and good practices in other countries. This should specify concrete examples, preferably from countries in Southeast or East Asia with similar levels of fiscal decentralization and development challenges

- Identification of issues related to accountability, transparency, participation, equity and parliamentary budget oversight in the current and draft law.

- Concrete suggestions for improving the draft law.

- Roadmap for follow-up assistances that UNDP and other development partners can provide to CFBA regarding the draft revised budget law and its implementation.

- Preparation of necessary presentations, based on the above policy notes, and presenting at various workshops on the revised budget law organised by the Committee on Financial and Budgetary Affairs for members of parliament or at other relevant fora.

- Development of a joint UN (possibly joint Development Partners- DP) policy note on the draft budget law.

In addition, the national specialist is expected to:

Coordinate with the Project Management Unit to organise consultations with key stakeholders to finalise the above policy notes. Consultations should include members of the law drafting board, members of National Assembly Committee on Financial and Budgetary Affairs, Committee on Economic Affairs, provincial Departments of Finance, provincial councils’ Commissions on Economic and Finance, key national research institutions such as Central Institute for Economic Management (CIEM), National Institute for Finance (NIF), as well as the World Bank and other development partners and NGOs working on public finance related issues. Coordinate with UNDP Programme Officer to establish contact  with relevant UN agencies working on the revision of the budget law for consultations at all stages of this process.

Arrange quality translation for the presentations and policy notes.

III. CONTRACT SUPERVISION

The work of the national public finance specialist will be supervised by international specialist, National Project Director (NPD) and UNDP Governance Unit Head. He/she will work in close consultation with National Project Manager, UNDP Policy Advisors (Economics and Public Administration Reform), UNDP Senior Technical Advisor and UNDP Programme Officer on parliamentary development.

IV. LOCATION OF WORK

Hanoi with some travel to provinces (where the workshop convenes). See details below in the schedule of work.

V. SCHEDULE OF WORK

The duration of this consultancy is up to 30 days as below.

| Activity | Duration | Time |
| --- | --- | --- |
| Support the analysis of the current budget law as well as various available drafts of the revised budget law | 3 days | Dec 2013 |
| Support the development of a report and an executive summary based on the above analysis and provide recommendations for amendments of the proposed revised budget law. | 3 days | Jan – Feb 2013 |
| Coordinate consultations with key stakeholders | 3 days | Feb – Mar 2014 |
| Support the preparation of various presentations based on the above policy notes and present at various workshops on the revised budget law organised by the Committee on Financial and Budgetary Affairs for members of parliament or other relevant fora | 4 days | Jan - May 2014 |
| Support the international specialist in providing guidance to the field work with NGOs. | 7 days | Jan - May 2014 |
| Support the development of a joint UN (possibly joint Development Partners-DP) policy note on the draft budget law. | 3 days | Jan - May 2014 |
| Support the finalisation of reports and joint UN or DP policy note. | 2 days | June - Oct 2014 |
| Arrange and quality check the translation for the presentations and policy notes. | 5 days | Oct 2014 |
| Total | 30 days |  |

VII. SCHEDULE OF PAYMENT

Tentative contractual period is from December 2013 to October 2014 with up to  30 working days.  Payment will be made upon satisfactory assessment of work by NPD,UNDP Head of Governance  Unit and international specialist at the completion of milestones of expected deliverables as follows: *

| Date | Payment (% of contract) | Deliverables |
| --- | --- | --- |
| Contract signing | 10% |  |
| 31 March 2014 (tentatively) | 40% | - Draft report and an executive summary based on the above analysis and provide recommendations for amendments of the proposed revised budget law. - Consultations with key stakeholders to finalise the above report. |
| 30 May 2014 (tentatively) | 40% | - Review of NGOs’ proposed workplan supporting the revision process of the law,conceptualise a field work process that engages NGOs and provide overall guidance to this field work process with NGOs - Joint UN (possibly joint Development Partners-DP) policy note on the draft budget law. |
| 30 Sept 2014 | 10% | - Preparation of presentations based on the above policy notes and present at various workshops on the revised budget law organised by the Committee on Financial and Budgetary Affairs for members of parliament or other relevant fora - Necessary adjustment and complete reports and joint UN/DP’s policy notes based on the official draft revised budget law (to be released in June 2014) |

* Travel cost for possible trips outside Hanoi will be covered separately when occur.

- Required Competencies and Qualifications

Competencies:

- Strong analytical and research skills;

- Excellent organisational and planning skills;

- Pro-active;

- Results-driven, and ability to meet strict deadlines.

Qualifications:

- Post-graduate degree in public finance, macro-economics, public administration, law, institutional/organisational development or related field or equivalent work experience;

- A minimum of 7 years working experience in the area of finance and budget, and specific experience in public finance management;

- Extensive knowledge of budget cycle, the work of parliamentary budget committees, parliamentary budget oversight processes in Vietnam.

- Work experience in public finance/institutional reform for other development partners in Vietnam is an asset.

- Work experience with civil society, media and National Assembly in Vietnam in promoting equity, transparency and accountability for government’s public finance management policies and programmes;

- Excellent spoken, report writing and presentation skills. Proficiency in English is an advantage.

- SUPPORTING DOCUMENTS

- TOR of the International Public Finance Specialist

- Current and draft State Budget Law

- Related workplan for supporting the revision of State Budget Law of NGOs led by Oxfam Great Britain

- Relevant documents from UN agencies and development partners

- Other relevant available documents

- Consultancy RATE and Requirements for submission of applications

“2012 EU-UNDP Guidelines for Financing Local Costs in Development Cooperation with Vietnam” will be applied for consultancy rate.

Interested individual consultants must submit the following documents/information to demonstrate their qualifications:

- Letter of Interest: explaining why they are the most suitable candidate for the work; providing a brief overview on how they will approach and conduct the work;

- CV, including past experience with similar type of work and the names of three references;

Applications should be sent to:

Mr Tran Thanh Dung

Project Manager

Project “Strengthening the Capacities of Budget Oversight for People’s Elected Bodies in Vietnam”

8 Chu Van An, Ba Dinh, Hanoi

Vietnam

Emails:

To:  dungcfba@gmail.com; project50739.vn@undp.org

Cc : bui.phuong.tra@undp.org

Closing date for applications:   5PM, 6 December 2013, Hanoi Time

Please note that applications should be sent to all above emails and only short-listed candidates will be notified.