English version below/Xin xem bản tiếng Anh phía dưới

Điều khoản tham chiếu

Tư vấn tổ chức tập huấn “Cha mẹ giúp con hướng nghiệp”

Dành cho cán bộ cấp cơ sở của Hội Liên hiệp Phụ nữ Việt Nam

Vị trí:	Chuyên gia tư vấn trong nước chuẩn bị tài liệu và tập huấn

Ngày bắt đầu:	19/03/2014

Địa điểm:	Hà Nội và TP Hồ Chí Minh

Thời gian:	08 ngày từ tháng 3 – tháng 4 năm 2014

Người giám sát:	Đào Thị Vi Phương, TW Hội LHPN VN và Nguyễn Thị Thủy, VVOB Việt Nam

1. THÔNG TIN CHUNG

Hội LHPN Việt Nam là tổ chức chính trị - xã hội tuyên truyền nâng cao năng lực và trình độ mọi mặt của phụ nữ nói chung và cũng như kĩ năng giáo dục và nuôi dạy con nói riêng, bao gồm cả năng lực hướng nghiệp thông qua thực hiện đề án chính phủ số 704 “Giáo dục 5 triệu bà mẹ nuôi dạy con tốt giai đoạn 2010 – 2015”.

Trong công tác hướng nghiệp cha mẹ đóng một vai trò rất quan trọng nhưng lại thiếu kiến thức và kĩ năng phù hợp.

Trong năm 2013, TW Hội LHPNVN với sự hỗ trợ của tổ chức Hợp tác phát triển và Hỗ trợ kỹ thuật vùng Flamăng (VVOB Việt Nam) đã xây dựng sổ tay “Cha mẹ giúp con hướng nghiệp” trong đó có giới thiệu lý thuyết hướng nghiệp và hướng dẫn cha mẹ áp dụng lý thuyết vào thực tiễn. Cuốn sổ tay này được gắn kèm với một bộ đĩa VCD và MP3 minh họa lý thuyết hướng nghiệp với các câu chuyện thực tế cộng với câu hỏi thảo luận. Những tài liệu này được phân bổ rộng rãi toàn quốc trong khuôn khổ đề án 5 triệu bà mẹ.

Trong kế hoạch hoạt động năm 2014 Trung ương Hội LHPN Việt Nam (TW Hội LHPNVN) phối hợp với tổ chức VVOB Việt Nam tổ chức Lớp tập huấn dành cho cán bộ nòng cốt của Hội LHPN Việt Nam nhằm tăng cường năng lực cho các bậc cha mẹ để hỗ trợ công tác hướng nghiệp cho con em. Hiện Hội LHPN Việt Nam tìm kiếm 01 chuyên gia tư vấn trong nước để tổ chức khóa tập huấn và điều hành tập huấn “Cha mẹ giúp con hướng nghiệp” cho cán bộ nòng cốt cấp cơ sở của Hội LHPNVN tại 14 tỉnh điểm với các thông tin như sau:

Mục tiêu lớp tập huấn:

Sau khoá tập huấn, học viên có thể:

- Hiểu được lý thuyết hướng nghiệp cơ bản và cách áp dụng

- Có khả năng hướng dẫn truyền đạt cho các bậc phụ huynh tại các CLB cha mẹ về nội dung và cách áp dụng lý thuyết này vào thực tế tại từng địa phương

- Có khả năng tổ chức các hoạt động tuyên truyền về Hướng nghiệp tại cộng đồng, bao gồm giới thiệu tài liệu Hướng nghiệp (sách, bộ đĩa VCD).

Thời gian và số lớp tập huấn:

- Thời gian tập huấn: Tháng 4/2014 (dự kiến từ 5 – 19/4/2014)

- Số lớp và số ngày tập huấn: 02 lớp tập huấn sẽ được tổ chức tại Hà Nội và Tp Hồ Chí Minh, mỗi lớp 2 ngày

Đối tượng tham dự:

Cán bộ Hội LHPN tại 14 tỉnh điểm triển khai đề án 704, mỗi tỉnh gồm 01 cán bộ Hội cấp tỉnh và 2 cán bộ cấp xã/thành viên Ban chủ nhiệm CLB Nuôi dạy con tốt. (khoảng 30 người/lớp)

2. MỤC TIÊU VÀ PHẠM VI TƯ VẤN

Công việc tư vấn này nhằm chuẩn bị và tổ chức tập huấn tại TP Hồ Chí Minh và tại Hà Nội (mỗi lớp 2 ngày). Nhiệm vụ của tư vấn còn bao gồm phát triển và xây dựng gói tập huấn bao gồm những tài liệu tập huấn đã có sẵn và tài liệu mới nếu cần để hỗ trợ cho hoạt động tập huấn.

3. PHƯƠNG THỨC LÀM VIỆC

Tư vấn được chọn sẽ phối hợp với TW Hội LHPNVN và VVOB Việt Nam chuẩn bị chương trình chi tiết và tài liệu tập huấn cho tập huấn giảng viên nguồn.

Kế hoạch tập huấn bao gồm một số các hoạt động được xác định rõ và phù hợp với chủ đề, bao gồm nhưng không giới hạn các yếu tố sau:

- Khung thời gian

- Tài liệu cần

- Mục tiêu

- Quy trình

- Đánh giá

- Tổng hợp kế hoạch hoạt động sau tập huấn

Tập huấn sẽ dựa trên cách tiếp cận có sự tham gia.

4. TRÁCH NHIỆM VÀ KHUNG THỜI GIAN

Tư vấn sẽ có những nhiệm vụ cụ thể sau:

| NHIỆM VỤ |  |  |  | ĐẦU RA |
| --- | --- | --- | --- | --- |
|  | Tháng 3 | Tháng 4 |  |  |
| 1. Chuẩn bị đề cương tập huấn Tư vấn sẽ chuẩn bị đề cương tập huấn trong đó nêu rõ cách tiếp cận, mục tiêu, các loại hoạt động và các loại tài liệu cần sử dụng. Đề cương sẽ được đưa ra thảo luận với TW Hội LHPNVN và VVOB Việt Nam, sau đó Tư vấn sẽ bổ sung các ý kiến đóng góp và phản hồi. | 1 ngày |  |  | 1.1. Đề cương tập huấn bao gồm gợi ý về cách tiếp cận, mục tiêu, hoạt động và tài liệu tập huấn 1.2. Đề cương cuối cùng có tổng hợp ý kiến đóng góp từ TW Hội và VVOB |
| 2. Chuẩn bị kế hoạch tập huấn và tài liệu tập huấn Tư vấn sẽ chuẩn bị một bản kế hoạch và tài liệu tập huấn chi tiết dựa vào đề cương tập huấn đã được thống nhất ở trên. Bước này cũng bao gồm việc soạn thảo các tài liệu cho người học sẽ được sử dụng để hỗ trợ tập huấn (bao gồm cả bài trình bày, nếu có) Bản thảo kế hoạch sẽ được thảo luận với VVOB và tư vấn sẽ bổ sung vào bản kế hoạch các ý kiến đóng góp và phản hồi. | 2 ngày |  |  | 2.1. Bản thảo kế hoạch tập huấn 2.2. Bản hoàn chỉnh kế hoạch tập huấn 2.3. Bộ tài liệu hỗ trợ tập huấn |
| 3. Điều hành tập huấn ở TP Hồ Chí Minh và Hà Nội (mỗi hội thảo tập huấn kéo dài 2 ngày) Tư vấn sẽ điều hành hội thảo tập huấn theo kế hoạch tập huấn đã được thống nhất |  | 4 ngày |  | 3.1. Tập huấn được tiến hành |
| 4. Chuẩn bị báo cáo Tư vấn sẽ viết một báo cáo về hội thảo tập huấn, đặc biệt đề cập tới các yếu tố sau: giới thiệu ngắn gọn về bối cảnh, các mục tiêu, mô tả thành phần học viên, chương trình tập huấn và hội thảo tập huấn đã được diễn ra như thế nào, các quan sát và đánh giá, kết luận và các điểm lưu ý. Tư vấn sẽ bổ sung nhận xét và phản hồi của TW Hội LHPNVN và VVOB nếu cần |  | 1 ngày |  | 4.1. Bản thảo báo cáo tập huấn 4.2. Bản hoàn chỉnh báo cáo tập huấn |
| Tổng |  | 8 ngày |  |  |

Tất cả sản phẩm đầu ra sẽ được viết bằng tiếng Việt.

5. TRÌNH ĐỘ CHUYÊN MÔN, KINH NGHIỆM VÀ NĂNG LỰC

- Bằng sau đại học về Giáo dục hoặc một lĩnh vực có liên quan được bổ sung bởi kinh nghiệm phù hợp trong ngành giáo dục

- Có kiến thức sâu về các vấn đề liên quan đến hướng nghiệp tại Việt Nam

- Kĩ năng phân tích và điều hành tốt

- Có kinh nghiệm làm việc với cộng đồng và Hội LHPNVN

- Nhạy cảm giới trong hướng nghiệp

6. MỨC THANH TOÁN

Thù lao sẽ được tính theo định mức áp dụng cho Chuyên gia cấp Quốc gia và Tư vấn cấp Quốc gia trong bản Định mức Chi tiêu của Liên minh châu Âu – Liên Hợp Quốc (EU/UN Cost Norms).

Các ứng viên quan tâm cần gửi 01 bản đề xuất trong đó nêu rõ phẩm chất năng lực liên quan, đề xuất kế hoạch công việc chi tiết, yêu cầu chi phí và sơ yếu lý lịch tới địa chỉ: hoanganhvwu@yahoo.com  hoặc Ban Gia đình Xã hội, Hội Liên hiệp Phụ nữ Việt Nam, 39 Hàng Chuối, Hà Nội.

Hạn cuối nhận hồ sơ là 17:00 ngày 13/03/2014

Hội Liên hiệp Phụ nữ Việt Nam giữ quyền sở hữu tất cả các dữ liệu do chuyên gia tư vấn thu thập và xây dựng trong quá trình thực hiện hợp đồng tư vấn. Mọi vấn đề liên quan đến phát hành hay công bố kết quả cần phải được sự chấp thuận của Hội.

Terms of Reference

Consultancy assignment: Provision of National training “Parents support children with career guidance” to the grassroot core trainers of Women’s Union (WU)

Function title:	National consultant to prepare and facilitate a training

Starting Date:	19 March 2014

Place:	Ha Noi and Hochiminh city

Timeframe:	08 days during March - April 2014

Supervision:	Dao Thi Vi Phuong, National WU and Nguyen Thi Thuy, VVOB Vietnam

- BACKGROUND

Vietnam Women’s Union is a mass organization that enhances and promotes women’s capacity and development nationwide in general and parenting skills in particularly, which also includes child support with career guidance (CG) through the 704 National Programme,also known as the 5 million mothers programme between 2010 and 2015. Parents play a very important role in supporting their children with career guidance, however, they lack knowledge and skills on career guidance.

In 2013 National WU developed a handbook “Parents support children with career guidance” supported by The Flemish Association for Development Cooperation and Technical Assistance (VVOB Vietnam) which includes introduction of Career Guidance theories and guidance for parents how to adapt these theories in the practices. The handbook is enclosed with a set of VCD and CD illustrating CG theories with real stories and follow-up questions for discussion. These materials are distributed nationwide within the framework of the National Program on capacity building of 5 millions mothers.

In 2014, national WU in collaboration with VVOB Vietnam organises a training based on available materials for WU’s members at grassroots level in the 14 pilot provinces of the National program.

Therefore we are seeking for a consultant to prepare and facilitate the training “Parents support children with career guidance” to the grassroots core trainers of Women’s Union with the following details:

Training objectives:

After the training, trainees are expected to:

- Understand the basic CG theories and how to put the theories into practice

- Be able to guide parents who are club members with the CG theories and how to apply the theories in the community

- Be able to organize community-based communication activities on career guidance, including introducing CG materials (handbooks, VCD sets)

Time and number of training workshops

- Time: April/2014 (from 5-19/4/2014)

- Number of days and training workshops: A two-day training workshop will be organized in Hanoi and Ho Chi Minh City.

Participants:

01 provincial WU staff and 02 communal WU staff/club board members of 14 pilot provinces of the 5 million mothers program (about 30 participants/workshop)

- OBJECTIVE AND SCOPE OF THE CONSULTANCY

The consultancy aims to prepare and deliver a 2-day training, duplicated in Hochiminh and Hanoi city for the core trainers at the grassroots level of the pilot 14 provinces.

The consultancy also includes to develop and compile a training package consisting of existing and, if needed, new training materials, to support the training activities.

- METHODOLOGY

The selected national expert will collaborate with National Women’s Union and VVOB Vietnam to prepare the detailed agenda, training materials for a ToT training.

The training plan will consist of a number of well defined and aligned activities, including but not restricted to the following elements:

- Timeframe

- Needed materials

- Objective

- Procedure

- Evaluation

- Planning “follow-up” after training

The training will apply a participatory approach.

All training documents will be prepared in Vietnamese.

4. RESPONSIBILITIES AND TIMEFRAME

The specific tasks for the expert are as follows:

| TASK |  |  |  | OUTPUT |
| --- | --- | --- | --- | --- |
|  | March | April |  |  |
| 1. Preparation of training outline The expert will prepare a rough outline of how she/he would approach to training, what objectives to use, which and which type of activities to conduct and which materials to use. The training outline will be discussed with National WU, VVOB Vietnam then the expert will incorporate comments and feedback. | 1 day |  |  | 1.1. Written draft training outline including suggested approach, objectives, activities and training material(s). 1.2. Final training outline including comments and feedback from National WU and VVOB Vietnam. |
| 2. Preparation of training plan and training materials The expert will prepare a detailed training plan based on the agreed training outline. This step also includes the preparation of the learning materials to be used to support the training (including PowerPoint slides, if applicable). A draft plan will be discussed with National WU and VVOB Vietnam and the expert will incorporate comments and feedback. | 2 days |  |  | 2.1. Draft training plan 2.2. Final training plan 2.3. Set of materials supporting the training |
| 3. Facilitation of 2 trainings in HCM and Hanoi city (2 days per each training) The expert facilitates the training according to the agreed training plan. |  | 4 days |  | 3.1. Training conducted |
| 4. Preparation of reports The expert will prepare a short report of the training, typically addressing the following elements: short intro setting the context, objectives, description of the type of participants, agenda and how the training actually took place, observations and evaluation, conclusion and points of attention. The expert will include comments of feedback of National WU and VVOB Vietnam draft report, if needed. |  | 1 day |  | 4.1. One draft training report 4.2. One final training report |
| Total |  | 8 days |  |  |

All outputs will be submitted in Vietnamese, in writing.

5. QUALIFICATIONS, EXPERIENCE AND COMPETENCIES

- Post-graduate degree in education or a related field complemented with relevant experience in the education sector

- Substantive and demonstrated knowledge of issues related to career guidance in Vietnam

- Strong analytical and facilitation skills

- Previous experience in working with the community and WU

- Gender sensitive in career guidance.

6. REMUNERATION

The remuneration is based on fees for National Experts and National Consultants in the UN- EU Guidelines for Financing of Local Costs in Development Co-operation with Vietnam.

Interested candidates are invited to submit 01 proposal which clearly states relevant expertise/experiences, detailed workplan and budget plan and other background information to hoanganhvwu@yahoo.com or by mail to Department of Family and Society, Vietnam Women’s Union, 39 Hang Chuoi Street, Hanoi. The deadline for submission is 17:00 of March 13, 2014.

Vietnam Women’s Union retains the intellectual property of all data collected and produced as part of this consultancy.  Prior permission to publish or present findings arising from this consultancy must be obtain.