| TERMS OF REFERENCE |  | THE LOVE JOURNEY PROJECT |
| --- | --- | --- |

| Project | Schools-based Project on Primary Prevention of Gender-based Violence in Da Nang City (The Love Journey) |  |  |
| --- | --- | --- | --- |
| Country Director Programme Manager | Ms. Elena Cristini |  |  |
| Consultant position | Technical consultant |  |  |
| Required task | To modelize and document the implementation process of the Love Journey project and to create a good practice for learning and sharing project’s achievement. |  |  |
| Assignment area | Da Nang city, Vietnam |  |  |
| Starting date | September 7th | Ending date | October 31st |

- Background on the assignment

Paz y Desarrollo (PyD) is a Spanish International NGO working in 14 countries around the world. PyD is supporting the implementation of a 4 -year regional programme on Economic Empowerment with gender perspective in Vietnam, Cambodia and East Timor.

In Vietnam, PyD is the organisation that jointly manages The Love Journey (Hanh Trinh Yeu Thuong): Danang Schools-based Gender Equity and Gender Violence Prevention Project with the Danang Department of Education and Training (DOET). The objective of the project, the first school-based prevention initiative, is to prevent gender-based violence before it occurs. PyD is doing this through a primary prevention strategy by encouraging gender equitable attitudes among boys and girls, promoting critical reflection on harmful gender stereotypes and building key relationship and life skills.

The Love Journey’s violence prevention curriculum has been adapted from the Gender Equity Movement in Schools project from the International Center for Research on Women (India).  Since 2012, the adapted project had been piloted in 10 secondary schools with pre-adolescent boys and girls (11-14 years of age) in Da Nang city. In 2014, with agreement and support from DOET, the Love Journey was extended the number of school participating in the pilot project to 20 schools more.

During 2 year of implementation in 30 secondary schools in Da Nang, the project has contributed to raise awareness on GE and GBV prevention and build skills on exercising healthy relationships, conflict resolutions and emotions/anger control among more than 12,000 boys and girls of age 11-14 through implementing 22 lesssons of the Love Journey curriculum and organizing communication activities. Other main activities of the project are capacity building for master trainers and teachers, implementation of the Safe School policy and counselling at schools. Along with those activities, the Love Journey has also produced thousands of communication materials and leaflets to introduce the project and to provide information and tips on GE, GBV prevention and building healthy relationships for students; developed manuals and guidlines on counselling services, safe school policy documents and positive disciplines alternative to violence to be distributed to teachers, educational staffs and parents.

In 2015, as the Love Journey project has come to the phasing out period, there is a need to modelize and document the implementation process of the Love Journey project and to create a good practice for learning and sharing the project’s achievment. The documentation of the project also aims to build evidence on a sucessful model of GBV prevention for any future adaptation or informing any intervention project on prevention of GBV in Viet Nam or any country in the world.  To carry out this task, an external consultancy is required.

- General objectives of the assignment

To modelize and document the implementation process of the Love Journey project and to create a good practice for learning and sharing project’s achivement.

- Specific objectives

- To review all documentation of the project such as successful stories, reports of trainings/wsk/evaluation, proposal, IEC materials, ect.

- To design tools and conduct fied trip to work with teachers, students, project staffs and partners to explore the information about the implementation process, experiences, lesson learnt and best practices of the Love Journey project.

- To develop the first draft of documentation.

- To organize a meeting with PyD staff and partners for comments, suggestions and improvements of the documentation.

- To revise, collect feedback and finalize the documentation.

- To translate the documentation into English.

- Scope of work, deliverables and timeline

| Scope of work | Deliverables | Deadline |
| --- | --- | --- |
| Review all documentation of the project such as successful stories, reports of trainings/wsk/evaluation, proposal, IEC materials, ect | An overview of all successful process of implementing the project, good practices and good models, lesson learnt and other achievement will be completed | 2nd w of Sep |
| Design tool of IDI and FGD and finalize the tool | A tool of conducting documentation will be finished | 3rd w of Sep |
| Trip 1: Field visit for interviews and focus group discussions with teachers, pupils, project staff and partners | A series of IDI and FGD will be conducted with teachers, pupils, PyD and partners' staff | 3rd w of Sep |
| Develop the first draft of documentation | The first draft of documentation developed. | 4th w of Sep |
| Trip 2: Meeting with PyD staff and partners for comments in Da Nang | A dissemination and consultation meeting organized. | 1st w of Oct |
| Revise the documentation, collect feedback and finalize the documentation | A final version of documentation in Vietnamese. | 2nd w of Oct |
| Translate the documentation into English | English version of the documentation | 31st of Oct |

- Management mechanism:

- The technical consultant and his/ her local research team will be under direct supervision of PyD project coordinator and will be providing frequent update information to PyD along the whole process, and submit fortnightly reports to PyD on the status of the work.

- It’s also required that the technical consultant and his team share all the outputs and deliverables of the work to PyD.

- All communication among the technical consultant and PyD made will be following online collaboration protocols developed by the consultant and PyD that ensure real-time access to data.

- Compensation

- The proposed budget for the consultancy for this assignment should NOT be more than 188,000,000 VND including value added tax, personal income tax and all expenses related to the consultancy.

- Requirement:

- Master degree or PhD in gender, sociology, social work or related field

- Minimum 5 years of experience in conducting gender research and project documentation

- Familiarity with GBV and gender issues and the Love Journey project activities, components and process.

- Excellent writing and reducting skills.

- High level of collaboration and flexibility for any technical requirements and modifications during the process.

- Application submission

Interested research institutes/organisations and individual consultants/teams of consultants must submit a consultancy proposal (key tasks, work plan, timelines and budget), curriculum vitaes of the proposed consultants and a cover letter in an envelope marked “Confidential” and ‘Application for modelization and documentation of The Love Journey Project’s implementation process” Room 101, 34 Ha Thi Than, Son Tra ditrict, Da Nang city or preferably via email to Ms. Pham Hong Thanh, Project Officer: Pham.thanh@pazydesarrollo.org. The application should be submitted in English.

Only short-listed institutes/organisations/firms and individual consultants with teams will be contacted. PyD reserves the right to select institutes/individuals prior to the closing date.

Notice: There is no application, processing or other fee at any stage of the application process.

Closing time for application is on September 4th , 2015.