CATHOLIC RELIEF SERVICES – VIETNAM PROGRAM

- Terms of Reference

FACILITATE TRAINING

Participatory action training on adaptive and protective measures of typical natural hazards (drought, salinity…) for local government staff

Project: Building resilience to natural hazards in Mekong River Delta Vietnam (1409/8960095)

- May-June, 2018

- Introduction:

Catholic Relief Services (CRS), Vietnam program, in collaboration with Tien Giang province is supporting the community driven Disaster Risk Reduction (DRR) plan and its implementation to increase the resilience of disaster-prone central coastal communities to natural hazards via the project “Building Resilience to Natural Hazards in Mekong River delta community Vietnam”. The project aims to develop the disaster risk reduction (DRR) and climate change adaptation (CCA) capacity of a range of stakeholders through a sustainable partnership to enhance safer and resilient communities in Quang Nam province of Vietnam.

The Decision 1002 on Community-based disaster risk management (CBDRM) has been issued since 2009. However, the CBDRM activities have been implemented in 1677 communes only with the results of 168 disaster risk maps produced.

Prior to this activity, the project communes have completed the CBDRA assessment and NDPC plan development in May. As one of the activity, the “Participatory action training on adaptive and protective measures of typical natural hazards (drought, salinity…) for local government staff will be carried out to raise the awareness for the community as linkages to the outcome of 1002 Government program

External trainer with expertise on the communication thematic issues will be recruited to carry out the session.

Within this TOR, a trainer will be invited to conduct the tasks of

- Training on PAOT approach, introduction steps to implement the PAOT activities at community

- Develop mini PAOT material to use at Tien Giang

- The objectives

The objectives of the assignment is to introduce the participants who are ward People’s Committees (CWPC) on PAOT approach and applying the PAOT in community communication

- Training content

3.1 Training participants

The participants are members of newly established TSGs and Community groups at the commune level by the local People’s Committee under the National 1002 CBDRM program includes representatives of Commune Committee for Natural Disaster Prevention(NDPC), mass organizations (MO), such as the Red Cross, Vietnam Women’s Union (VWU). These participants have received the two training courses on CBDRM/CBDRA and conducted CBDRA to their communes, developed CBDRA report and NDPC plan.

- District Office of Agriculture and Rural development: 1 persons (1 per/district)

- Representative from commune Committee of NDPC: 8 per each commune in which 3 of the following members should be in the list

  - Commune accountant

  - Vice Chairman of the Commune People Committee

  - Commune People Committee officer

- Community representative: 1 cluster head from each ward

3.2 Content:

Task 1: 1st training course

- Providing foundational background PAOT approach and good practices in application of approach in DRR communication to LGA, MO, CBOs staff and commune leaders, specifically members of TSGs and CGs just established.

3.3 Expected result:

After the training, the participant will

- Familiarize the TSGs to the PAOT DRR material

- By the end of the training, the participants familiarize with PAOT approach and

- Have knowledge of steps on PAOT communication at their community

- Able to organize and facilitate the PAOT training at their community

- Able to build a detailed operation plan for PAOT activities for their ward

- Scope of work

4.1 Pre-Training activities: Before conducting the training the trainer will carry out the following key pre-training activities including:

  - Collection and review of key supporting materials/information relevant to the objectives/topic of the training activity consisting of PAOT material

- Develop the mini appropriate materials for the training course and reference document to hand-out to participants.

- Collect and review key supporting material (session plan, training PowerPoints) in order to design of the programme/materials for the training activity (or updating of or adjustment to the requirements/objectives of the training activity; etc...)

3.2 Conduct training courses

- Cooperate with CRS to develop training agenda to meet above objectives.

- Develop training facilitation guide using CRS provided format for the training based on developed contents and methodology.

- Prepare training materials (hand-outs, text, slides, reference document, video/clips…) for distribution during the training.

- Facilitating training in order to meet outcomes expectation including the plan of communication applying PAOT.

- Develop simple pre-test and post-test (no more than 1 page)

- Analyzing pretest, posttest and writing report in Vietnamese

### 3.2 Post training, follow-up activities

### -     Location and timeline

| Activity | Timeline | Location | Working days |
| --- | --- | --- | --- |
| Review all available materials by DMC (Directorate of government, MARD other INGOs, NGO and recommended by MARD to develop the appropriate materials for the workshop and reference document to hand-out to participants. | May 2018 | Hanoi | Consultant: 1 day |
| Develop the short PAOT material to use |  |  | Consultant: 2.5 days |
| Training materials development including training agenda, facilitation guideline, Training presentation/ handout, video/clips, pre and post-test in line with CRS branding and marking policy | May 2018 | Hanoi | Consultant: 1 day |
| Training course to TIen Giang | 24 May 2018 (Tentative) | Thang Binh, | Consultant: 1 day/district |
| Summarize pre and post-test and writing report | May 2018 | Hanoi | Consultant: 0.5 day |
| Total working days for consultant |  |  | 6 days |

- Deliverables

- Set of training material  including handout, presentation reading material distributed to  participants, list of reference material suggested, in Vietnamese

- List of participants attended with result of pre and post test

- Photos of the workshop

- Report in Vietnamese submitted with the which include

    - Evaluation on the participants

    - Lessons learnt on how to improve the sessions for better organizing next activities.

- 1 Communication plan develop by the ward

- Requirements

- Extensive experience in carrying out training/facilitating PAOT on DRR

- Sound knowledge and skills in applying PAOT approach in DRR

- Understanding government DRR policies, programs and guidelines related to CBDRM/DRR.

- Experience in participatory facilitation skills

- Excellent writing and analytical skills

- The trainers who are experience in PAOT material development is an asset thus will be encouraged to apply