EXTERNAL EVALUATION TERM OF REFERENCE

Vietnam Country Program

| Project name and location | Agro-Climate Forecast and Information System for Enhanced Community Resilience (ACF Project) |
| --- | --- |
| Project duration | Phase 1: July 2018 – Sep 2019 Phase 2: Jan 2020 – Sep 2020 |
| Project sector | CCA |
| Implementing Agency | Catholic Relief Services |
| Donor Funding Source | Catholic Relief Services |

This Terms of Reference (TOR) contains the information related to the consultant-led documentation and learning for the project Agro-Climate Forecast and Information System for Enhanced Community Resilience conducted by CRS Vietnam Country Program.

The consultant-led work aims to i) Document learning and evidence from agro-climate forecast project (in a way that can be externally shared); and ii) Explore and advise on future applications and/or opportunities for CRS to take this work forward with further small scale financial investment.

I. PROJECT BACKGROUND

CRS and Implementing Partners

Catholic Relief Services (CRS) is a US non-governmental organization that has been operating in Vietnam since 1994. CRS projects assist local counterparts to build capacity in the areas of  Mine Risk Education, Disability, Disaster Risk Reduction, and Emergency Preparedness and Response.

In 2018, CRS built an innovative partnership with Center for Hydro-meteorology, Environmental Training and Technology Application (HYMETECH), a government agency under Vietnam Meteorological and Hydrological Administration, Ministry of Natural Resource and Environmenti. This partnership focused on the development of agro-climate forecasts (monthly, quarterly and seasonal) and related recommendations on crop-calendar. This partnership aimed to promote and enhance collaboration modalities between specialized national institutes and related units at regional and provincial level. In addition, CRS cooperated with Dien Ban and Thang Binh People’s Committee as key implementing partners for the ACF Project.

Project Goal and Objectives

The “Agro-climate forecast and information system for enhanced community resilience” project was implemented in Dien Ban Town and Thang Binh District in Quang Nam province with the goal: “Women and men of coastal rural communities in Thang Binh district and Dien Ban town protect livelihoods from climatic disaster risks”; and strategic objective: “Women and men of vulnerable coastal rural communities in Thang Binh district and Dien Ban town have reduced loss of their crops from climatic disaster risks”. This project was conducted in two phases. In order to achieve the strategic objective, the project focused on below key actions:

Phase I: July 2018 – September 2019.

- Enhance accessibility to information on hydro-meteorology and seasonal calendar through providing adequate device/facility and strengthen the capacity of farmers via community based organizations (CBOs) e.g. common interest groups, farmer cooperatives to understand demand and seek for agro-climate forecast information services, application of scientific and low-cost appropriate technologies contributing to delivery adequate and timely hydro-meteorology and seasonal calendar to end-users;

- Partnership development and building the capacity of provincial Hydro-meteorology Stations in gathering, analyzing and sharing weather information (particularly for district and commune level accuracy) which result in the mechanism to collect, gather, consolidate and analyze and deliver/disseminate the climate forecast information and seasonal instructions together with DARD system;

- Build the capacity of provincial DARD, Thang Binh DARD, Dien Ban Economic Department in translating weather forecasts timely and providing practical advisoriesfor farmers, on how to adjust their crop calendar and farming system to sustain the 2-way mechanism;

- Keep the momentum of existing partnership with Thang Binh DARD, Dien Ban Economic Department and continuity to sustain the partnership with them to combine scientific and local knowledge and test forecast technology using a bottom-up approach as creating a 2-way communication mechanism (information system), allowing farmers to receive and provide their feedback and recommendations on the accuracy of given predictions (shape the information);

Phase II: Jan 2020 - Sep 2020

- Having continuous collecting data for the year 2 for more reliability of evidence-based MEAL data

- Addressing learning questions and gaps during the implementation of phase I as well as Including the Regional Technical Advisor’s comments in the project plan

- Ensuring the sustainability of the agro-climate forecast model via:

  - Strengthening attitude and practices of farmers in applying agro-climate forecast advisories

  - Supporting local partner to advocate the necessity of agro-climate forecast services in the context of climate changes to relevant sub-national government agencies;

  - Supporting partner to prepare proposals and defend annual budget in front of Department of Planning and Investment as well as People’s Council

  - Leveraging those relationships to improve partners’ performance at scale while CRS withdraws gradually financial support

II. PURPOSE OF THE EVALUATION

The purpose of this evaluation is to document learning and evidence from the agro-climate forecast model and explore on future applications and/or opportunities for CRS to take this work forward.

III. EVALUATION SCOPE AND TIME FRAME

The intended time frame for the entire consultancy for evaluation purposes is expected to run no more than total 35 days for all consultant’s team leader and member(s). The desk assessment and completion of evaluation plan should be completed and shared CRS before deployment to collect field data. Total of 3 project communes in Dien Ban Town (2) and Thang Binh District (1) will be visited to have a range of responses.

The consultant team will be expected to present their interim findings following field data collection and final presentation at the end of the project with related stakeholers. Key activities are including but not limited to the followings:

- Desk review of all related documents.

- Interview with DRR PM and virtual interview with key project stakeholders

- Develop Detailed Evaluation Plan and Methodology to submit to CRS before deployment

- Collect datas in 3 project communes. Includes a presentation of interim findings after the field work.

- Write final report, including final presentation of results at the end of the project and  responding to CRS comments and revision.

In the event of COVID-19 transmission increasing in Vietnam, the evaluation will adopt alternative approaches complying with CRS’ COVID-19 MEAL guidance and regulations of the Vietnam government. Timeframe and methods will be adusted accordingly to ensure quality and efficiency of the consultancy.

IV. STAKEHOLDERS IN THE EVALUATION

The consultant will work primarily with the CRS Vietnam MEAL Manager, who will lead on overseeing the work and supporting the consultant as needed.

Key stakeholders in the evaluation include:

- CRS: DRR Team, Country Manager, and DRR/CCA Regional Technical Advisor

- Department of Agricultural and Rural Development (DARD)

- Center for Hydro - Meteorological Technology Applications   (HYMETECH)

- Provincial Hydrometeorology Station

- Commune People Committees in project sites

- Farmers who were involved in the 4 models

- Communities in project sites

V. EVALUATION QUESTIONS

Questions of this evaluation are divided between the two purposes i) document learning and evidence from the agro-climate forecast model; ii) recommend for future applications and/or opportunities for CRS.

1. Document learning and evidence:

- What does the customized climate information system model look like?

  - Along the crop cycles, how the different climate forecasts (7-day, 15-day, monthly, 3-6months) affected decisions  and changes taken for rice, corn, peanut and seasame crops?

  - Which stakeholders are involved and what are their roles in the chain of crop collection, production, communication, use and beneffiting?

- Is the model relevant to communities’ adaptation and management of climate risks?

- What will be motivation of the communes to continue with this activity after project closure?

- How does this model support improved yields, productivity and eficiency for women and men in vulnerable coastal communities?

- What role have women and men in the community played in generating, analysing and translating the agro-climate forecast information for actionable decision-making? (e.g. shaping preferences, needs, formats). Are there any gender differences, specific barriers, or enabling factors in this?

- What are community and stakeholder reflections on the accessibility, reliability and use of climate information generated?

- What are the successful lessons and good practices that the model has brought about for the women and men of coastal rural communities in Thang Binh and Dien Ban town in climate risk management and production protection?

- What sustainability can be seen from the project?

- To what extent the authority is continuing their activities?

- How is the post-project maintenance of hardware?

- How successful were the project efforts of capacity building for HYMETECH, DARD and local farmers/committees?  To what extent to they need to be sustained?

- Which organisations were engaged in institutionalization of the project?

2. Recommendation for CRS future application/opportunites:

- What issues or results have emerged during implementation that may influence possible future programming?

- What were the key enabling and inhibiting factors that influenced quality implementation of the activities and achievement of project?

- What relevant practices have been applied and adopted by the local authorities and/or government bodies? What are the pre-conditions for this?

- What does external environment including both GoV landscape (policies, initiatives, etc) and relevant donors include that is relevant to this work in Vietnam? How does the CRS project align with this?

- What other actors are leading projects or initiatives similar to this in Vietnam?

- Where should CRS invest resources into furthering this work, including but not limited to: technical skills and programmatic approaches and activities?

- What partnership and/or funding opportunities might be available for CRS in future agro-climate work?

- What are the most viable scalability/replicability pathways (e.g. scale out to include more farmers in same agro-climate zone with existing equipment; replicate in a different zone with new equipment; vertical insitutionalisation with goverment)

VI. EVALUATION METHODOLOGY

The consultant, in discussion with Head of Program and Meal Manager, will determine appropriate data sources and methods/tools of assessment. Generally, the assessment will comprise the following methods:

- Desk review. This will include documentation provided by CRS including project data, as well as documents identified and sourced by the consultant related to GoV, donor and other organisation policies, studies, initiatives, etc. relevant to agro-climate work.

- Key informant interviews (KII)

- Group discussion

- Household visits (4 models)

VII. EXPECTED DELIVERABLES

Consultant(s) is expected to deliver three deliverables during the contract period:

i) Detailed Evaluation Plan and Methodology

ii) Agro-climate Forecasting Project Learning and Evidence Report

iii) CRS Recommended Next Steps Report

- The Detailed Evaluation Plan and Methodology will be drafted by the consult and submitted to CRS for review and comments by 30 June 2021. This should include:

- Key considerations  including alignment with relevant national and global best practices such as Global Framework for Climate Services.

- Qualitative/Quantitative evaluation methods

- Evaluation schedule

- Data Analysis methodology and framework

- Evaluation Criteria, Questions simplified for the field

- Evaluation Questions, Methodologies, Sources and Tools

- Questions for each stakeholder group

- Other key information specific to this evaluation: budget plan, etc.

- Recommended Outlines for the Learning/Documentation Report and Analysis Report

- The Agro-climate Forecasting Project Learning and Evidence Report submitted to CRS for comments and review by 31 August 2021.  This report is expected to be no longer than 20 pages (excluding appendices), and should be written and presented in standard form to enable CRS to share internally and externally.  Sources should be cited consistently, using a globally recognized format.

- The CRS Recommended Next Steps Report will be submitted to CRS for comments and review by 31 August 2021.  This is a CRS internal document, and should not exceed 7 pages, excluding appendices.  Sources should be cited consistently, using a globally recognized format.

VIII. CONSULTANT QUALIFICATION

The consultant will be selected based on adequate skills, experience, and qualifications.

- Master’s Degree required, PhD preferred.

- At least seven years of experience designing and conducting evaluations for learning/documentation for international NGOs

- Experience in Climate Change Adaptation is required, and knowledge in Agro-climate forecast is a plus.

- The ability to respectfully and effectively communicate with diverse groups of people.

- Strong interpersonal and facilitation skills, and cultural and gender sensitivity in working with local communities and a range of stakeholders.

- Excellent oral communication skills and the ability to deliver high quality written reports in English and Vietnamese.  (Note: The TOR deliverables will be produced in English only, however interviews and many government source documents will be in Vietnamese).

- Excellent analytical and writing skills

- Demonstrable experience in producing high-quality, credible evaluations, documentation

IX. LOGISTICAL SUPPORT

The following support will be provide to the consultant by CRS:

- Available project documentation including approved project design phase 1 and 2, logbooks, reports, project brochure.

- Transport, accommodation, meals and other logistical considerations to be coordinated by CRS Vietnam or consultant (s) upon the agreement of two parties during consultant recruitment and contract signing.

- Interviews and meetings with project participants, government officials at province, district and commune level, DARD, HYMETECH,  CRS staff, households and communities will be coordinated by CRS Vietnam in consultation with consultant

X. KEY TERMS AND CONDITIONS

- Payment will base on submission of tax Invoice on delivery against milestones agreed  between CRS and Consultant.

- Travel, meal, & accommodation costs and other expenses related to the assignment in the project site except where otherwise stated in the Terms of Reference above will be provided by CRS to nominated bank account upon receiving invoice and receipts.

- All equipment and materials required for the assignment are to be provided by the contractor except where otherwise indicated in the Terms of Reference above.

- CRS may request written evidence of necessary insurance (including workers’ compensation & personal indemnity), superannuation, and taxation prior to commencement of the assignment.

XI. APPLICATION PROCEDURE

Interested parties are requested to submit in English:

- Expression of Interest (1 page maximum)

- A concise technical proposal (2 pages maximum)

- A tentative work plan with indicative budget (2 pages maximum)

- CVs demonstrating relevant capacity and experience

- Minimum 2 references for similar assignment

- Example of previous similar work (weblink or PDF)

Applications should be sent in sealed envelope (hard copy, duly signed) to the following address:

CATHOLIC RELIEF SERVICES

R. 301-303, Building E3, Trung Tu Diplomatic compound, No. 06 Dang Van Ngu, Dong Da Dist., Hanoi, Vietnam

Attn: Ms. Tran Thi Thu Hang – Admin Officer

Tel: 024 3773 8300

Deadline for submission: 09 May 2021

Only shortlisted applicants shall be contacted for interview before contracting.

***Our Catholic identity is at the heart of our mission and operations. Catholic Relief Services carries out the commitment of the Bishops of the United States to assist the poor and vulnerable overseas. We welcome as a part of our staff people of all faiths and secular traditions who share our values and our commitment to serving those in need. CRS’ processes and policies reflect our commitment to protecting children and vulnerable adults from abuse and exploitation.

CRS is an Equal Opportunity Employer